## Summary
Central Deposit: Task Matrix Summary (v3)
Counts update automatically from the Phase 1 and Phase 2 sheets.
Status | Phase 1 | Phase 2 | Total
Not Started
Ready for Dev
Open Question
Not Scoped
Confirmed Phase 2
Done
Total
Priority | Phase 1 | Phase 2 | Total
High
Medium
Low
Total
Change in v3 | Phase 1 | Phase 2 | Total
New
Updated
Total

## Phase 1
Central Deposit: Task Matrix, Phase 1 (v3)
Core request management, workflow, notes, Beluga reference, podcast publication and approval. v3 adds the 23/09 requirements review. Fill in the yellow Deliverable Date cells. Columns K and L (23/09): what the app delivers today (version) and what is still missing.
ID | Category | Task / Requirement | Priority | Status | Depends On | Deliverable Date | Source | Change in v3 | Notes | Built in app (version) | What is missing
P1-01 | Requestor Communication | Add an editable requestor notes field usable during the review process. Notify the admin whenever the requestor adds a new comment. Include a hint explaining what the field is for. | Medium | Ready for Dev |  |  | Unhappy Path Doc, Q1 | Updated | IT confirmed it, including the hint. v3: overlaps with the request level notes in P1-27 (admin field, email alert, Last updated on). Best built together as one piece of work. | v20/v23: per-media-file Notes (CI_Notes, Info tab) with hint "Anything Central Deposit should know about this media file". Stays editable for the requestor while Processing and saves by itself. | A request-level requestor notes field (build with P1-27). Notification to the admin when the requestor adds a comment.
P1-02 | Notifications | Automatic cancellation of stale requests: cancel after 3 months in the cycle, with a reminder sent every month until then. | High | Ready for Dev |  |  | Unhappy Path Doc, Q2 |  | IT confirmed. | — | Not built in the app. Needs a scheduled Power Automate flow (cancel after 3 months, monthly reminder).
P1-03 | Sorting / Display | Sort pending requests by publication date (soonest first) and by creation date (oldest first). Confirm the publication date field exists. | Low | Open Question |  |  | Unhappy Path Doc, Q2 |  | Still open: IT repeated the question instead of answering it. | Request Management sorts by Created (newest first); the ReviewScreen queue by Modified. | Decision still open. Pick the date: the requests list has PublishedDate, StartRequestDate and EndRequestDate; media files have PublicationStartDate.
P1-04 | Notifications | Send a notification whenever an admin reopens (un-approves) a Published request. | Medium | Not Started |  |  | Unhappy Path Doc, Q4 |  |  | v11: Published status retired (RS_BtnPublish hidden). | Decide whether this still applies now Published is retired. Notification not built.
P1-06 | Status Workflow | Define the final status list: new Under Review status after submission, and whether Pending becomes Attention Required (or Rejected becomes Incomplete). | High | Open Question |  |  | Unhappy Path Doc, Q7 | Updated | IT marked this TBD. v3: the 23/09 review adds a Partially approved outcome (P1-35) and talks about requests being approved (P1-32), while the current revision dropped Approved in favour of Processing. Settle the full status list in one decision, since P1-32 and P1-35 depend on it. | v11: Draft → Processing (acts as Under Review) → Approved / Rejected / Pending. Pending = Need info, requestor resubmits. Published retired. v44: Reject writes Rejected, Need info writes Pending. | Final naming (Under Review vs Processing, Attention Required vs Pending) and a Partially approved status (P1-35).
P1-07 | Notifications | Notify the admin when a request stays in Under Review for more than 1 week. | Medium | Not Started | P1-06 |  | Unhappy Path Doc, Q7 |  |  | — | Not built in the app. Needs a flow on Processing requests older than 7 days.
P1-08 | Workflow | Allow the requestor to cancel or re-route a request stuck in review for more than 1 week. | Medium | Not Started | P1-06 |  | Unhappy Path Doc, Q7 |  |  | — | Not built in the app.
P1-09 | Assignee / Hand-off | Support assignee hand-off between admins and notify the newly assigned admin. | Medium | Open Question |  |  | Unhappy Path Doc, Q7 |  | IT answered with a question ("Right?"), needs a clear yes. | ReviewScreen assignee picker (RV_Assignee); approver / co-assignee saved on Approve. Assignee shown and filterable on Request Management. | Hand-off at any time (not only on Approve) and a notification to the newly assigned admin.
P1-10 | Automation | Auto-delete drafts left untouched for 1 week. | Medium | Ready for Dev |  |  | Unhappy Path Doc, Q8 |  | Confirmed twice by IT. | — | Not built in the app. Needs a scheduled flow.
P1-11 | Validation | Block the Draft to Under Review transition when mandatory fields are empty. | High | Done |  |  | Unhappy Path Doc, Q11 |  |  | v12: Submit / Resubmit stay disabled until title, DG, both contacts and valid media are complete. v35: fixed the values they read. | —
P1-12 | Validation / UX | Show a message listing which required fields or attachments are missing. | Medium | Done |  |  | Unhappy Path Doc, Q12 |  | IT says it already works this way. Quick check before closing. | RS_LblMissing ("Still to complete") on the request, CL_LblMissing on the Legal tab, and the checklist on the Validations tab. | —
P1-13 | Notifications | Notify the requestor whenever their request status changes. | High | Done |  |  | Unhappy Path Doc, Business Questions |  | Already working as described. | Nothing in the app sends notifications (no mail connector); assumed to be an existing flow. | Confirm the flow covers the current statuses: Processing, Pending, Rejected, Approved.
P1-14 | Beluga Reference | Add a Beluga reference (I-number) field per media file on ChildMetaScreen, for all production types (photo reportage, video, podcast). Visible and searchable by admins. | High | Done |  |  | Unhappy Path Doc + Requirements review 23/09 (item 3) | Updated | v3: moved from one field per request (at Published) to one field per media file, confirmed in the review. Open point: should requestors see it once the file is published? | v15/v17: Beluga reference per media file (CI_BelugaRef), admin-only, shown once the request is Approved. v14: admin Beluga search box on Request Management. | It sits on the Info tab (ChildInfoScreen), not ChildMetaScreen. Open point: requestors do not see it.
P1-15 | Audit | Activity log with a full audit trail per request (nice to have). | Low | Open Question |  |  | Unhappy Path Doc, Other topics 5 |  | IT: TBD. The deleted request audit trail is already in Phase 2 (P2-04). | — | Not built in the app.
P1-16 | Bug Fix | Contract Case 2 label should read "Direct Service Contract". | High | Ready for Dev |  |  | Unhappy Path Doc, Other topics 6 |  | IT confirmed. | — | Not done: the Contract case list still reads "Case 2 - specific service contract" (Case 1 reads "framework / direct service contract"). Confirm the wording; one-line change in CL_Case.Items.
P1-17 | Rights & Declarations | Add a "No third-party rights" option (radio button) in Rights & Declarations. | Medium | Done |  |  | Unhappy Path Doc, Other topics 6 |  | IT confirmed. | v19/v21: "No third-party rights in this production" in Rights & declarations, saved to NoThirdPartyRights. | Built as a checkbox, not a radio button.
P1-18 | Bug | Assignee field doesn't work after approval and doesn't show in the requests gallery. | High | Done |  |  | Alexander, new item |  |  | v10/v17: Assignee picker fixed; Approve writes Assignee; Assignee column and filter on Request Management. v39: Person value format fixed. | Confirm in testing: approve a request, then check the Assignee column in the list.
P1-19 | UX Enhancement | Add a button on the Review Screen to improve the review experience (scope to confirm). | Medium | Not Started |  |  | Alexander, new item |  |  | ReviewScreen gained Need info (v11), Internal Notes with a save icon per media row (v34) and a queue that reloads after each action (v41). | Scope still to confirm: which button was meant.
P1-20 | Requestor Field Logic | Requestor field: pre-select and lock the current user for Requestors. For Admins, show all requestors with "All" as default. | Medium | Done |  |  | Alexander, new item |  |  | v10: requestor filter pre-selects and locks the current user for REQUESTOR; ADMINISTRATOR gets all requestors, with "All" as default. | —
P1-21 | UX | Request Management screen opens with sections expanded by default. | Low | Not Started |  |  | Alexander, new item |  |  | — | Not done: the filter sections still open collapsed (locShowFilters starts false).
P1-22 | UI Layout | Left-align the Request Title and DG fields. | Low | Not Started |  |  | Alexander, new item |  |  | — | Not changed in the app. Confirm the target layout.
P1-23 | UI Layout | ID field at 30% width, Title field at 70%. | Medium | Not Started |  |  | Alexander, new item |  |  | Request Management: Request ID box 280 px and Title box 579 px (about 33/67), on separate rows. | Confirm whether 30/70 side by side is wanted.
P1-24 | UI / Content | New Request screen: review the screen title (scope to confirm). | Low | Not Started |  |  | Alexander, new item |  |  | The card title switches between "New request" and "Request details" by status. | Scope still to confirm.
P1-25 | UX | Add a Save button alongside Submit, visible but disabled until applicable, to guide the user. | Medium | Done |  |  | Alexander, new item |  |  | v12: Draft Save always visible next to Submit, disabled until title and DG are filled. v35: fixed what it saves. | —
P1-26 | UI Styling | Style the Add Media button to match the Submit button. | Low | Not Started |  |  | Alexander, new item |  |  | v12 restyled it, but the current app has "+ Media" orange (RGBA 180, 95, 6) while Submit is blue (RGBA 56, 96, 178). | Not done in the current app: set RS_BtnDraftSave_1 colours to match Submit.
P1-27 | Internal Notes | Two general internal notes fields per request: one for the Administrator, one for the Requestor. Send an email notification as soon as a note is added, and show "Last updated on" with the date of the latest change next to each field. | Medium | Ready for Dev | P1-01 |  | Alexander, new item + Requirements review 23/09 (items 2, 7) | Updated | v3: redefined from a single shared Notes field into two role based fields with email alerts and a last updated date. Open point: can the requestor read the Administrator's notes, or are they admin only? | v34/v43: Administrator notes box on the request screen (RS_AdminNotes, saved to ReviewerComments). Editable by ADMINISTRATOR, read-only for REQUESTOR with a placeholder. | Requestor request-level notes field. Email notification when a note is added. "Last updated on" date next to each field.
P1-28 | Validation / Permissions | While a request is Under Review, lock it to view only for the requestor, except the notes field (P1-01), which stays editable. | Medium | Done | P1-01 |  | Unhappy Path Doc, Q3 |  | From IT's green comments. | v13/v23: requestor view-only while Processing on every tab; Notes stays editable. v32: the attachments form follows the same lock. | —
P1-29 | Validation | The requestor can never set the Published status. Only Central Deposit (Admin) publishes. | Medium | Done |  |  | Unhappy Path Doc, Notification & Awareness |  | From IT's green comments. | v11: Published retired and the publish button hidden; no requestor path can set it. | —
P1-30 | Notifications / Reporting | Automated follow-up email every 5 business days summarising stuck or at risk requests. | Medium | Ready for Dev |  |  | Unhappy Path Doc, SLA |  | From IT's green comments. | — | Not built in the app. Needs a scheduled flow.
P1-31 | Internal Notes | Decide whether each media file needs its own internal notes field for the requestor. If yes, add it to ChildMetaScreen for all production types. | Low | Open Question | P1-27 |  | Requirements review 23/09 (item 1) | New | Asked as an open question. The request level notes in P1-27 may be enough; a field on every media item adds clutter. | Per-media-file Notes exist (Info tab) and are editable on ReviewScreen as "Internal Notes" (v34). | Decision still open. Internal Notes and the requestor's Notes are the same column, so they are not private.
P1-32 | Review / Publication | RequestDetailScreen gallery: once a request is approved, flag each media file still missing its Beluga reference. Add a Published checkbox on each row and a button to apply it to all rows at once or one by one. | Medium | Not Started | P1-14, P1-06 |  | Requirements review 23/09 (item 4) | New | Confirm which screen "RequestDetailScreen" refers to (RequestScreen or ReviewScreen in the current app). The Published checkbox can also feed partial approval in P1-35. | — | Not built in the app.
P1-33 | Podcast | Podcast type: allow publication on Spotify as well as Beluga (publication channel field). Add attachments for the podcast photo, each episode photo and the audio file. Show a link to the required photo dimensions next to the upload. | High | Not Started |  |  | Requirements review 23/09 (item 5) | New | The dimension rules themselves are now shown as labels (P1-37); the link can point to the fuller guidance. Confirm its URL and owner. Automatic dimension checking is in Phase 2 (P2-06). | Podcast visual and episode visual upload boxes exist, with helper labels (P1-37). | Spotify / publication channel field, audio file upload and the guidance link. The two uploads still save with Patch, which does not work for SharePoint attachments: move them to a form like CL_FormAttach.
P1-34 | Podcast / Data Model | Episodes in more than one language: decide how to capture them (one episode with several language versions, or one record per language) and which files each language needs. | Medium | Open Question | P1-33 |  | Requirements review 23/09 (item 6) | New | Worth settling in Phase 1 because it changes the episode metadata structure (spec 5.2). Changing it later means migrating existing episode records. | — | Decision still open.
P1-35 | Approval Workflow | Overall approval field on the request with a Partially approved option. The admin flags which media files will not be approved or published. On partial approval, send a notification listing which files were published. | High | Not Started | P1-06, P1-32 |  | Requirements review 23/09 (item 8) | New | Suggestion: derive it from the Published checkboxes in P1-32 (all ticked = Published, some ticked = Partially approved) so the admin doesn't set it twice. | — | Not built in the app.
P1-36 | Attachments | Proposal: one general attachment area per request, instead of relying only on per media file attachments, for files that repeat across media files. | Medium | Open Question |  |  | Requirements review 23/09 (item 9) | New | Raised for team agreement. Saves uploading the same file several times. Check how it fits with the contract checklist documents, which already sit at request level. | v32: attachments per media file through CL_FormAttach (Legal tab). | Request-level attachment area not built; decision still open.
P1-37 | Podcast / UX | Add helper labels next to the podcast image uploads so users see the requirements before uploading. Podcast visual (with text): square format, minimum 1400 x 1400 px and maximum 3000 x 3000 px, JPEG or PNG, RGB colour space. Episode visual: horizontal format, 1280 x 720 px, JPEG or PNG. | High | Done | P1-33 |  | Alexander, new item | New | Specs provided directly, so no decision needed. Same rules will drive the automatic check in P2-06, so keep them in one place (e.g. a config list) rather than hardcoded twice. | Helper labels CI_HintPodcastVisual (square, 1400-3000 px, JPEG/PNG, RGB) and CM_HintEpisodeVisual (1280x720, JPEG/PNG). | The rules are hardcoded in the two labels, not in one config list.

## Phase 2
Central Deposit: Task Matrix, Phase 2 (v3)
Reporting / Power BI, archiving, audit and recovery, and automated photo dimension checks. Fill in the yellow Deliverable Date cells. Columns K and L (23/09): what the app delivers today (version) and what is still missing.
ID | Category | Task / Requirement | Priority | Status | Depends On | Deliverable Date | Source | Change in v3 | Notes | Built in app (version) | What is missing
P2-01 | Archiving | Archive requests 3 years and older, accounting for the SharePoint 5,000 item list view threshold. | High | Ready for Dev |  |  | Unhappy Path Doc, Q1 |  | Stakeholders said 2 years, IT's later comments say 3. Using 3; confirm with IT. | — | Not built in the app.
P2-02 | Archiving | General archiving policy for older requests on the platform. | Medium | Ready for Dev |  |  | Unhappy Path Doc, Other topics 4 |  | Overlaps with P2-01, may be the same piece of work. | — | Not built in the app.
P2-03 | Reporting | Scope and build the Reporting / Power BI integration. | Medium | Not Scoped |  |  | Phase split |  |  | — | Not scoped or built.
P2-04 | Audit & Recovery | Audit trail for deleted requests with soft delete, so they can be recovered, including Published requests. | High | Confirmed Phase 2 |  |  | Unhappy Path Doc, Q6 |  | Moved from Phase 1 per IT. A red note called recovery "not the priority now"; check how firm that is. | — | Not built in the app.
P2-05 | Archiving | Auto-archive rejected requests after 30 days, giving the requestor time to respond. | Medium | Ready for Dev |  |  | Unhappy Path Doc, Q5 |  | From IT's green comments. | The Rejected status is written by the Reject button (v44). | Not built in the app. Needs a scheduled flow.
P2-06 | Podcast / Validation | Automatically check that uploaded podcast and episode photos meet the required dimensions, format and colour space (rules in P1-37), and warn or block when they don't. | Medium | Not Started | P1-33, P1-37 |  | Requirements review 23/09 (item 5) | New | Explicitly scheduled for Phase 2 in the review. | — | Not built in the app.